## Sheet1
Number | Done | Status | Description | Type | Importance | Timescale | Depends0 | Depends1
40 | Y | Done | create DOER | task | Primary | Days
39 | Y | Done | get android devices to test | task | Primary | Days | 40
41 | Y | Done | get ethics approval | task | Primary | Days | 40
7 | Y | Done | decide message/metadata format | task | Primary | Days
6 | Y | Done | design and implement a protocol for discovering nodes in close proximity and passing messages and necessary metadata between them. | objective | Primary | Weeks | 7
8 | Y | Done | design message passing protocol | task | Primary | Days | 7 | 9
9 | Y | Done | design message storage protocol | task | Primary | Days | 7
15 | Y | Done | Set up repository | task | Primary | Days
16 | Y | Done | Set up build | task | Primary | Days | 15
10 | Y | Done | implement message format | task | Primary | Days | 7 | 16
11 | Y | Done | implement message storage | task | Primary | Days | 9 | 16
13 | Y | Done | implement device discovery | task | Primary | Days | 16
12 |  | Ready | implement message passing protocol | task | Primary | Days | 8 | 13
19 | Y | Done | implement epidemic routing | task | Primary | Days | 16
18 | Y | Done | implement buffer eviction | task | Primary | Days | 19
17 | Y | Done | implement a simple epidemic routing algorithm to send message to all available nodes | objective | Primary | Days | 18 | 19
21 | Y | Done | Design encryption mechanism | task | Primary | Days
20 | Y | Done | Design a routing algorithm using user metadata to route messages while disguising message content and metadata | objective | Primary | Days | 21
44 |  | Ready | Poster | objective | Primary | Days | 20 | 6
24 |  | Ready | Design smartphone UI | task | Secondary | Days
23 |  | Blocked | Create a smartphone UI | objective | Secondary | Weeks | 24 | 14
28 | Y | Done | design trust mechanism | task | Secondary | Days
26 |  | Ready | Implement a more advanced routing algorithm | objective | Secondary | Weeks | 20
27 |  | Blocked | Implement a mechanism to decide whether a node is trustworthy or not | objective | Secondary | Weeks | 28 | 26
31 |  | Ready | Find users to participate | task | Secondary | Days
32 | Y | Done | send logs to a central server | task | Secondary | Days | 19
33 |  | Blocked | obtain performance data | task | Secondary | Weeks | 31 | 32
30 |  | Blocked | Evaluate the performance of the implemented routing algorithms | objective | Secondary | Weeks | 33
36 |  | Ready | set up simulation | task | Tertiary | Weeks
37 |  | Blocked | run simulation | task | Tertiary | Days | 36
35 |  | Blocked | Compare the real world vs simulated performance of the routing algorithms | objective | Tertiary | Weeks | 37
42 |  | Blocked | publish on app store | task | Tertiary | Days | 23
43 | Y | Done | publish on github | task | Tertiary | Days | 16
Primary | 89.47%
Secondary | 22.22%
Tertiary | 20%
Total | 60.61%