## Sheet1
Number | Status | Description | Type | Importance | Timescale | Depends0 | Depends1
40 | Ready | create DOER | task | Primary | Days
39 | Blocked | get android tablet | task | Primary | Days | 40
41 | Blocked | get ethics approval | task | Primary | Days | 40
7 | Ready | decide message/metadata format | task | Primary | Days
6 | Blocked | design and implement a protocol for discovering nodes in close proximity and passing messages and necessary metadata between them. | objective | Primary | Weeks | 7
8 | Blocked | design message passing protocol | task | Primary | Days | 7 | 9
9 | Blocked | design message storage protocol | task | Primary | Days | 7
15 | Ready | Set up repository | task | Primary | Days
16 | Blocked | Set up build | task | Primary | Days | 15
10 | Blocked | implement message format | task | Primary | Days | 7 | 16
11 | Blocked | implement message storage | task | Primary | Days | 9 | 16
13 | Blocked | implement device discovery | task | Primary | Days | 16
12 | Blocked | implement message passing protocol | task | Primary | Days | 8 | 13
14 | Blocked | Create a core library to manage message storage and routing | objective | Primary | Days | 16
19 | Blocked | implement epidemic routing | task | Primary | Days | 16
18 | Blocked | implement TTL | task | Primary | Days | 19
17 | Blocked | implement a simple epidemic routing algorithm to send message to all available nodes | objective | Primary | Days | 18 | 19
21 | Ready | Design encryption mechanism | task | Primary | Days
22 | Ready | Design routing algorithm | task | Primary | Days
20 | Blocked | Design a routing algorithm using user metadata to route messages while disguising message content and metadata | objective | Primary | Days | 21 | 22
24 | Ready | Design smartphone UI | task | Secondary | Days
23 | Blocked | Create a smartphone UI | objective | Secondary | Weeks | 24 | 14
28 | Ready | design trust mechanism | task | Secondary | Days
26 | Blocked | Implement a more advanced routing algorithm | objective | Secondary | Weeks | 20
27 | Blocked | Design and implement a mechanism to decide whether a node is trustworthy or not | objective | Secondary | Weeks | 28 | 26
31 | Ready | Find users to participate | task | Secondary | Days
32 | Blocked | send logs to a central server | task | Secondary | Days | 26
33 | Blocked | obtain performance data | task | Secondary | Weeks | 31 | 32
30 | Blocked | Evaluate the performance of the implemented routing algorithms | objective | Secondary | Weeks | 33
36 | Ready | set up simulation | task | Tertiary | Weeks
37 | Blocked | run simulation | task | Tertiary | Days | 36
35 | Blocked | Compare the real world vs simulated performance of the routing algorithms | objective | Tertiary | Weeks | 37
42 | Blocked | publish on app store | task | Tertiary | Days | 23
43 | Blocked | publish on github | task | Tertiary | Days | 23